## Sheet1
Daily Test Report
Sprint -11
|  | Start Date | 2017-01-11 |  | End Date | 15/11/2017
S.No | Requirement | Build Date | Deployed in QA | No'f TCs | No'f TCs Excuted | No'f TCs passed | No'f TCs failed | RAG Status | Comments
1 | UC-001 | 2017-11-05 | Yes | 30 | 10 | 9 | 1 | A | Defect 5677
2 | UC-002 | 2017-11-07 | no | 15 | 0 | 0 | 0 | R
3 | UC-003 | 2017-11-10 | no | 50 | 0 | 0 | 0 | G
4 | UC-004 | 2017-11-06 | yes | 25 | 25 | 25 | 0 | G | Testing complted
5 | UC-005 | 2017-11-12 | no | 100 | 0 | 0 | 0 | A | The No'f test cases required to excute more time
Note:No'f test cases are more,it requires more time