## Sheet1
Daily Test Report
Sprint -11
|  | Start Date | 2017-01-11 |  | End Date | 15/11/2017
S.No | Requirement | Build Date | Deployed in QA | No'f TCs | No'f TCs Excuted | No'f TCs passed | No'f TCs failed | RAG Status | Comments
1 | UC-001(Login Screen) | 2017-11-05 | Yes | 30 | 10 | 10 | 0 | G | Defect 5677-fixed
2 | IN-002(product details page) | 2017-11-07 | yes | 5 | 5 | 5 | 0 | G
3 | IN-012(payment process) | 2017-11-10 | yes | 11 | 11 | 10 | 1 | A | QA deployment delayed by one day Bug IN-12 raised.
4 | UC-004 | 2017-11-06
5 | UC-005 | 2017-11-12
Note:No'f test cases are more,it requires more time